## Inst-FR(JV)
サービス関連資料
設置時チェックリスト
MIMAKI ENGINEERING CO., LTD.
URL:http://www.mimaki.co.jp
D500986-10

## Inst-CG(JV)
サービス関連資料 > 設置時チェックリスト 変更履歴
設置時チェックリスト 変更履歴
年月日 | 2014.09.01 |  | ﾏﾆｭｱﾙ Ver |  | 1.00 | 備考
状況 | 索引 | Rev. |  | 変更内容
発行 |  |  |  | 初版発行
© 2014 MIMAKI ENGINEERING CO.,LTD. | [6 empty] | 設置時チェックリスト 変更履 | P.1

## Inst-CHK(JV)
設置時チェックリスト > CJV300 設置時チェックリスト | [15 empty] | Rev.
Model |  |  | CJV300 |  |  |  | Issued | 2014.09.01 | Revised | F/W ver. |  | 1.30 | Remark
CJV300 設置時チェックリスト | [15 empty] | 1.0
■ 切傷事故防止や、インクに触れないようにするため、分解組立作業時には必ず手袋を着用すること。 ■ 作業実施の際は、周囲に充分なスペースを確保し、安定した場所に設置すること。 ■ 本製品は、非常に重量が重いため、取り扱いには充分注意すること。
| 項目 |  |  |  |  | 外形寸法 (W×D×H) (mm) | [7 empty] | 重量 (kg)
| 梱包 |  |  |  |  | 160サイズ : 2,912x750x1,050 130サイズ : 2,662x750x1,050 | [7 empty] | 160サイズ : 235kg
130サイズ : 220kg
| 機械本体 |  |  |  |  | 160サイズ : 2,775x700x1,392 130サイズ : 2,525x700x1,392 | [7 empty] | 160サイズ : 178kg
130サイズ : 167kg
A) | 設置前の事前準備及び確認事項
本装置を設置する前に、以下の項目を必ず確認してください。
|  | 1. | □ | 設置場所確認
|  |  |  | □ | 設置場所の床平面度及び強度は問題がなかった。
*装置重量は 160サイズ：178kg、130サイズ：167kg
|  |  |  | □ | 設置場所は直射日光、振動、可燃物、ほこりがなかった。
|  |  |  | □ | 電気的ノイズ及び磁気ノイズが装置の仕様レベルである。
|  |  |  | □ | 設置環境は（温度が 20℃ から 30℃、湿度が 35% から 65%Rh、且つ、結露なきこと）である。
*精度保証温度は 20℃ から 25℃、温度勾配は ±10℃/h 以下
|  |  |  | □ | インクの保管場所は冷暗所である。
|  |  |  | □ | 装置の設置スペースは（前後が 1000mm 以上、左右が 500mm 以上）である。
|  |  |  | □ | 近くに化学物質がない。
|  |  |  | □ | 換気及び排気状況が良い。
|  | 2. | □ | 設置時の装置搬入経路及び開梱スペースがある。
|  | 3. | □ | 電源（AC100 - 120V / 220 - 240V ±10% x2 50/60Hz ±1Hz、アース “GND” ）が準備されている。
|  | 4. | □ | 使用パソコンはRIPの仕様範囲内。
|  | 5. | □ | インクの手配。
|  | 6. | □ | メンテナンス洗浄液の手配。 （ソルベントインク: SPC-0294: ヘッド洗浄カートリッジ、SPC-0369: ソルベント用メンテナンス洗浄液キット200） （昇華転写インク: SPC-0188S: ヘッド洗浄カートリッジ、SPC-0137: 洗浄液ボトルキットA29 ）
|  | 7. | □ | USB2.0ケーブルを準備。（ケーブルの長さ5m以内。延長する場合、リピーターケーブルを接続すること）
|  | 8. | □ | 使用メディアの手配。
|  |  |  | □ | 厚さが 1.0mm 以下である。
|  |  |  | □ | 重さが 40kg 以下、紙管内径は 2~3 インチ、ロール外形は直径250mm 以下である。
B) | 梱包状態及び付属品確認
設置作業を問題なく行うために、装置状態及び付属品を必ず確認してください。
|  | 9. | □ | 本体梱包箱、装置に破損または目立つ傷がなかった。
|  |  |  | □ | 問題があった場合、写真を撮り、設置レポートに添付すること。
|  | 10. | □ | 付属品の漏れがなかった。（「付属品リスト」を参照ください）
|  |  |  | □ | 問題があった場合、「付属品リスト」にマークし、設置レポートに添付すること。
C) | 装置の組み立て及び設置
次の手順で装置を確認しながら、組み立て及び設置を行ってください。
|  | 11. | □ | 脚と本体を組み立てる。
|  | 12. | □ | 付属品を取り付ける。
|  | 13. | □ | プリントヘッドのストッパを取り外す。
© 2014 MIMAKI ENGINEERING CO.,LTD. | [10 empty] | CJV300 設置時チェックリスト |  |  |  | R.1.0 | P.1
SS21:
4色: M,C,Y,K 各色2本
8色: M, C, Y, K, Lm, Lc, Or, Lk 各色1本
6色+Si, W: M, C, Y, K, Lm, Lc, Si, W 各色1本
6色+W: M, C, Y, K, Lm, Lc 各色1本 W 2本
Sb53:
4色: M,C,Y,K 各色2本
4色+Dk: M, B, Y, Dk 各2
6色: M, B 各2本 Y, K, Lm, Lb 各色1本
6色+Dk: M, B 各2本 Y, Dk, Lm, Lb 各色1本

## Inst-CHK (2_JV)
設置時チェックリスト > CJV300 設置時チェックリスト | [13 empty] | Rev.
Model |  |  | CJV300 |  |  | Issued | 2014.09.01 | Revised | F/W ver. |  | 1.30 | Remark
CJV300 設置時チェックリスト | [13 empty] | 1.0
■ 必ず本装置の近くにある電源コンセントに接続し、容易に取り外しができるようにすること。 ■ コンセントに差し込む際は、他の機器と別系統のコンセントに接続する。 消費電力が大きいため、供給電源のブレーカーが遮断する場合がある。 ■ 電源ケーブルは、アース処理されたコンセントに接続すること。 感電および本装置が破損する恐れがある。 ■ 電源ケーブルを接続する際は、本装置の電源スイッチをオフにしてから行うこと。
D) | 装置電源の投入及び装置準備
電源工事を行った後、以下の項目を行ってください。
|  | 14. | □ | インターフェイスケーブルの接続。（ケーブルの長さ5m以内。延長する場合、リピーターケーブルを接続すること）
|  | 15. | □ | 付属の電源ケーブルを接続し、電源ケーブルクランプでロック。
|  | 16. | □ | 装置電源をONにし、ファームウェアのバージョンを確認。
|  |  |  | □ | [FUNC1] + [FUNC3]キーにてサービスモードで電源投入すること。
|  |  |  | □ | 必要に応じて、[REMOTE]キーにて最新のファームウェアにアップグレードする。
|  | 17. | □ | 確認用メディアをセットし、メディア幅検出を実行。（メディアは 500mm 以上の幅が必要）
E) | インクの初期充填
使用するインク種類及びインクセットを確認し、以下を行ってください。
|  | 18. | □ | 充填するインクを確認後、カラー銘板を貼り付け。
|  | 19. | □ | ソルベントインク充填の場合、充填液を充填する。
|  | 20. | □ | LCD画面の指示に従い、インクセットを選択する。
|  |  |  | □ | 充填時に問題があった場合、状況を把握し設置レポートに記入すること。
|  | 21. | □ | 初期充填が終了後、テストプリントにてノズル状態を確認。
|  |  |  | □ | 必要に応じて、クリーニングを行い状況を把握し設置レポートに記入すること。
F) | 装置の機能確認
初期充填終了後、下記の項目を行い装置の基本動作を確認または調整してください。
|  | 22. | □ | [# チョウセイ] > [ ヘッドチョウセイ]>[ ドットイチ]>[ オウロ] および[ フクロ] を実行し、必要に応じて調整。
|  | 23. | □ | [ セッテイ] > [ ドットイチホセイ] を実行し、必要に応じて調整を行う。
G) | パソコン及びソフトウェアのセットアップ
パソコンをセットアップし、ソフトウェアをインストールしてください。
|  | 24. | □ | ミマキドライバーをインストール。
|  | 25. | □ | パソコンをセットアップし、RIPをインストール。
|  | 26. | □ | オンラインプリントの確認。
H) | パラメータのバックアップ
アフターサービスの問題対応等の為に装置パラメーターを保管してください。
|  | 27. | □ | 電源投入時の[▲] + [▼]キーにて装置パラメーターをアップロード。
I) | 装置の最終確認
本装置の最終確認のため以下の項目を確認してください。
|  | 28. | □ | 取り外したカバー類を取り付ける。
|  | 29. | □ | 装置の周り、表面カバーなどの汚れをきれいにする。
J) | ユーザー教育
設置終了後にお客様に対し、装置の基本的な操作及び情報に関する教育を行ってください。
|  | 30. | □ | 「安全上のご注意」に記載の装置を操作する上での危険性に関して教育を実施する。
|  | 31. | □ | 装置の基本仕様及びメディアのセット方法を説明。
|  | 32. | □ | 基本的なオペレーション機能を説明。
|  | 33. | □ | プリント条件の設定方法を説明。
|  | 34. | □ | インクの取り扱いについて説明。（MSDS、処分方法等）
|  | 35. | □ | 日常のお手入れについて説明。（理由、手順等）
© 2014 MIMAKI ENGINEERING CO.,LTD. | [9 empty] | CJV300 設置時チェックリスト |  |  | R.1.0 | P.2

## Inst-RPT(JV)
設置時チェックリスト > CJV300 設置レポート | [26 empty] | Rev.
Model |  |  | CJV300 |  | Issued | 2014.09.01 |  | Revised |  |  |  |  | F/W ver. |  |  | 1.30 |  | Remark
CJV300 設置レポート | [26 empty] | 1.0
■ | 必要事項を記入後、品質保証部へ送付願います。
（FAX：0268-64-5580、Email：qa-installation@mimaki.jp）
| 設置日 |  |  |  | 担当者 |  |  | 拠点名
| 年 月 日 | [6 empty] | □ | 札幌 | □ | 仙台 |  | □ | 東京 |  | □ | 埼玉 |  | □ | 長野
[8 empty] | □ | 名古屋 | □ | 金沢 |  | □ | 大阪 |  | □ | 広島 |  | □ | 福岡
| 機種 |  |  |  | シリアル番号 |  |  | 出荷時 F/W |  |  |  | 設置後 F/W | [5 empty] | インク種類 |  |  |  | インクセット
| CJV300 |  |  | □-130 □-160 |  |  |  | Ver. |  |  |  | Ver. | [5 empty] | □ |  |  |  | □ | 4 color |  | □ | 4 color+Dk
[22 empty] | □ | 8 color |  | □ | 6 color
[22 empty] | □ | 6 color+ W
[22 empty] | □ | 6 color+ Si,W
[22 empty] | □ | 6 color+ Dk
| RIP用パソコン（MIMAKI取り扱い） | [6 empty] | RIP用パソコン（購入品）
| □ ミマキ標準 □ ミマキハイスペック | [6 empty] | 型名：_________________________ | [6 empty] | CPU：_____________/_____________hz | [8 empty] | RAM：____________
PCシリアル番号 :
RasterLinkシリアル番号 :
□ 「安全上のご注意」に記載の装置を操作する上での危険性に関して教育を実施した
A) | □ | 設置が問題なく終わった
B) | □ | 設置場所を確認した
| 1. | 設置環境
|  | □ | 設置場所周辺に化学物質が置いてある。化学物質の種類は [ ] である。
|  | □ | 設置場所周辺にインク以外の不快臭がする。においの原因は [ ] である。
|  | □ | 次の情報を記入してください。
|  |  | ■ 環境温度 [ ] ℃ |  |  | ■ 環境湿度 [ ] %Rh |  |  |  |  | ■ 電源電圧 [ ] V
C) | □ | 設置時に対象となるFCOを実施した場合、記入して下さい
|  |  | FCO No |  |  |  | FCO内容 | [13 empty] | コメント
|  | □ | FCO
|  | □ | FCO
|  | □ | FCO
|  | □ | FCO
|  | □ | FCO
D) | □ | 設置時で問題があった（* 下記の中から不具合をチェックしてください）
| 1. | 梱包状態、付属品
|  | □ | 梱包箱に損傷がある。 [ □ 本体梱包箱 ]
|  | □ | 装置に破損、目立つ傷、汚れがある。[ □ 本体 , □ 脚]
|  |  | □ | 付属品リストにて確認し、漏れた部品にチェックを付けてこのリポートに添付すること。
| 2. | 電源ON、初期充填、装置の動作
|  | □ | 症状 (大まかな範囲でどの辺が悪かったのか症状を下記の図に示してください。)
| □ノズル抜け □飛行曲り □色混ざり | [5 empty] | □ノズル抜け □飛行曲り □色混ざり | [10 empty] | ■ | テスト作図を100%出力する為に
追加実施した項目
[19 empty] | □ | ソフトクリーニング[ 回]
[19 empty] | □ | キャップ調整[ メカ調整・オペ調整]
[19 empty] | □ | ノーマルクリーニング[ 回]
[19 empty] | □ | UISSバルブ周りの調整または交換
[19 empty] | □ | ハードクリーニング[ 回]
[19 empty] | □ | ヘッド交換
[19 empty] | □ | 清掃・手動クリーニング
[19 empty] | □ | その他[ ]
|  | □ | USBドライバ等の理由でPCとの接続がうまくできなかった
| 3. | 画質
|  | □ | 傾き調整の再調整が必要だった
|  | □ | フィード補正2（サービスモード）の調整が必要だった
|  | □ | その他調整を行った [ ]
© 2014 MIMAKI ENGINEERING CO.,LTD. | [16 empty] | CJV300設置レポート | [7 empty] | R.1.0 |  | P.1

## Inst-RPT (2_JV)
設置時チェックリスト > CJV300 設置レポート | [10 empty] | Rev.
Model |  | CJV300 | Issued | 2014.09.01 | Revised | F/W ver. | 1.30 |  | Remark
CJV300 設置レポート | [10 empty] | 1.0
E) | その他、要望などありましたら記入をお願いいたします
© 2014 MIMAKI ENGINEERING CO.,LTD. | [7 empty] | CJV300 設置レポート |  | R.1.0 | P.2

## Inst-FR-E(JV)
Service Documents
INSTALLATION CHECKLIST
MIMAKI ENGINEERING CO., LTD.
URL:http://eng.mimaki.co.jp/
D500987-10

## Inst-CG-E(JV)
Installation Checklist > Installation Checklist Change Tracking
Installation Checklist Change Tracking
Date | 2014.09.01 |  | Manual Ver. |  | 1.00 | Remark
Status | Index | Rev. |  | Changes
Released |  |  |  | New issue
© 2014 MIMAKI ENGINEERING CO.,LTD. | [6 empty] | Installation Checklist Change Tracking | P.1

## Inst-CHK-E(JV)
INSTALLATION CHECKLIST > CJV300 Installation Checklist | [15 empty] | Rev.
Model |  |  | CJV300 |  |  |  | Issued | 2014.09.01 | Revised | F/W ver. |  | 1.30 | Remark
CJV300 Installation Checklist | [15 empty] | 1.0
■ Always wear gloves during disassembly and reassembly to prevent cut accident or not to touch ink. ■ Install the printer on a firm floor with a sufficient work space around it. ■ Take great care not to suffer injury when handling the printer, which is very heavy.
| Item |  |  |  |  | Outer Dimensions (W×D×H) (mm) | [7 empty] | Weight (kg)
| Packaged |  |  |  |  | JV300-160 : 2,912x750x1,050 JV300-130 : 2,662x750x1,050 | [7 empty] | JV300-160 : 235kg
JV300-130 : 220kg
| Main Unit |  |  |  |  | JV300-160 : 2,775x700x1,392 JV300-130 : 2,525x700x1,392 | [7 empty] | JV300-160 : 178kg
JV300-130 : 167kg
A) | Advance preparations and points to be checked before installation
Be sure to check the following items before installing the printer.
|  | 1. | □ | Installation location.
|  |  |  | □ | No problems are found regarding floor surface and floor strength of the location.
*The weight of printer: 160size -178kg, 130size -167kg
|  |  |  | □ | The location is free from direct rays of the sun, vibration, combustible materials and dust.
|  |  |  | □ | The level of electrical and magnetic noise at the location meets the specifications.
|  |  |  | □ | Installation environment is to be set at 20 to 30 °C, 35 to 65% RH and non condensing.
*Accuracy of the printer can be assured at temperature ranging from 20 to 25 °C and temperature gradient not over ±10 °C/h.
|  |  |  | □ | Ink is to be stored at cool and dark place.
|  |  |  | □ | The space with more than 1,000 mm long in both the front and back and with more than 500 mm long in both the right and left is left after having installed the printer.
|  |  |  | □ | There is not a Chemical material near.
|  |  |  | □ | Both air infiltration and exhaust ventilation at the installation location are adequate.
|  | 2. | □ | Both carry-in route of the printer and space to unpack it are sufficiently secured before its installation.
|  | 3. | □ | Electrical power supply (AC100 - 120V / 220 - 240V ±10% x2 50/60Hz ±1Hz, with ground “GND” installed) is available.
|  | 4. | □ | The personal computer. used with the printer conforms to the specifications for the software RIP and cutting software.
|  | 5. | □ | Prepare ink cartridges.
|  | 6. | □ | Prepare the maintenance cleaning liquid.
Solvent ink: (Use SPC-0294: MS Cleaning Cartridge, SPC-0369: Cleaning solution kit 200)
Sublimation ink: (Use SPC-0188: Washing Liquid cartridge, SPC-0137: Cleaning-Solution Bottle kit A29)
|  | 7. | □ | Prepare USB2.0 Cable. (Cable length of 5m or less. To extend the cable, connect a repeater cable.)
|  | 8. | □ | Prepare applicable printing media.
|  |  |  | □ | Thickness of the media is 1.0 mm or less.
|  |  |  | □ | The weight is 40kg and below, the inside diameter of the paper core is 2 to 3 inches and the external diameter of the roll is 250mm and below in diameter.
B) | Check on printer packaging condition and the accessories
Be sure to check the condition of the printer and its accessories so that you can install them smoothly.
|  | 9. | □ | No damage or conspicuous scratches are found on the packing boxes for the main body and its legs, as well as the main body itself.
|  |  |  | □ | If any problems are found, take pictures of the problem areas and attach them to “Installation Report”.
|  | 10. | □ | Whether there is any missing accessory. (See “Accessories List”.)
|  |  |  | □ | If any problems are found, check-mark the “Accessories List” and attach the list to “Installation Report”.
C) | Assembly of the printer and its installation
Assemble and install the printer in accordance with the following procedures while checking each component.
|  | 11. | □ | Assembling the stands and the device.
|  | 12. | □ | Mounting the accessories.
|  | 13. | □ | Remove the “head stopper”.
© 2014 MIMAKI ENGINEERING CO.,LTD. | [10 empty] | CJV300 Installation Checklist |  |  |  | R.1.0 | P.1
SS21:
4-colors: M,C,Y,K, 2 cartridges for each color
8-colors: M,C,Y,K,Lm,Lc,Or,Lk, 1 cartridges for each color
6-colors+Si, W: M,C,Y,K,Lm,Lc,Si,W, 1 cartridges for each color
6-colors+W: M,C,Y,K,Lm,Lc, 1 cartridges for each color/ W, 2 cartridges
Sb53:
4-colors: M,C,Y,K, 2 cartridges for each color
4-colors+Dk: M, B, Y,DK 2 cartridges for each
6-colors: M, B 2 cartridges for each Y,K,Lm,Lb, 1 cartridges for each color
6-colors+Dk: M, B 2 cartridges for each color Y, Dk, Lm, Lb 1 cartridges for each color

## Inst-CHK-E (2_JV)
INSTALLATION CHECKLIST > CJV300 Installation Checklist | [12 empty] | Rev.
Model |  |  | CJV300 |  |  | Issued | 2014.09.01 | Revised | F/W ver. | 1.30 | Remark
JV300/JV300A Installation Checklist | [12 empty] | 1.0
■ Make sure that the printer is connected to an electrical outlet located in its vicinity so that the outlet can be unplugged easily. ■ When putting a electrical plug from the printer into an outlet, do not use an outlet that is connected to other equipments. Otherwise the circuit breaker may be disconnected due to a large electric power consumption of the printer. ■ Connect to power cable to a grounded electrical outlet to avoid an electrical shock or printer breakage. ■ Be sure to turn off the power switch of the printer when connecting the power cable from the printer to an electrical outlet.
D) | Application of power and preparation for printing operation
Carry out the followings after an electric power supply work is completed.
|  | 14. | □ | Connect the interface cable to the printer. (Cable length of 5m or less. To extend the cable, connect a repeater cable.)
|  | 15. | □ | Connect the power cable provided as an accessory to the printer.
|  | 16. | □ | Turn on the power switch of the printer and check the version of firmware.
|  |  |  | □ | Turn on the power switch through the service mode using [FUNC1] and [FUNC3] keys.
|  |  |  | □ | Upgrade the firmware to the latest version using [REMOTE] key when necessary.
|  | 17. | □ | Set up printing media for testing and check the media width. (The media shall be 500 mm or more in width.)
E) | Initial charge of ink
Carry out the followings after checking type of ink and ink-set to be used.
|  | 18. | □ | After checking the type of ink to be charged, attach color label to the cartridge BKT.
|  | 19. | □ | When using the solvent ink, fill up the pre fill up solution.
|  | 20. | □ | Following instructions on LCD, choose the ink set,
|  |  |  | □ | If any problems are found during the charge, grasp the situation correctly and fill it in “Installation Report”.
|  | 21. | □ | After the initial charge is completed, check the conditions of nozzles by pressing the key [TEST PRINT].
|  |  |  | □ | Perform [CLEANING] if needed, to grasp the condition of the printer, then fill it in “Installation Report”.
F) | Check of the printer functions.
|  | 22. | □ | Perform [#ADJUST] > [HEAD ADJUST] > [DROP.POS ADJUST] > [YSi] and [YRe], and adjust as required.
|  | 23. | □ | Press the key [SET UP], then [DROP.POScorrect] to make adjustments when necessary.
G) | Setting up of the personal computer and software
Set up the personal computer and install software.
|  | 24. | □ | Install the Mimaki Driver.
|  | 25. | □ | Set up the personal computer and install RIP.
|  | 26. | □ | Check the print quality online.
H) | Backup of parameters
Back up the printer parameters to deal with problems, etc. in after-sales service.
|  | 27. | □ | Upload the printer parameters using keys [p] + [q] when power switch gets turned on.
I) | Final check
Check the following items to finish the machine installation.
|  | 28. | □ | Attach all removed cover back to the machine.
|  | 29. | □ | Clean around the machine and the machine cover surface.
J) | User training
Give customers instructions concerning basic operation and information of the printer after installation.
|  | 30. | □ | Perform the education about the risk on the operation of machine described in “ Safety Precautions ”.
|  | 31. | □ | Give instructions concerning basic specifications of the printer and the method of setting up printing media.
|  | 32. | □ | Give instructions concerning basic operation function of the printer.
|  | 33. | □ | Give instructions concerning the condition setting for printing.
|  | 34. | □ | Give instructions concerning the handling of ink (including instructions concerning MSDS and disposal methods).
|  | 35. | □ | Give instructions on daily maintenance of the printer (including reasons and procedures for the maintenance).
© 2014 MIMAKI ENGINEERING CO.,LTD. | [9 empty] | CJV300 Installation Checklist |  | R.1.0 | P.2

## Inst-RPT-E(JV)
INSTALLATION CHECKLIST > CJV300 Installation Report | [23 empty] | Rev.
Model |  |  | CJV300 |  | Issued | 2014.09.01 |  |  | Revised |  |  | F/W ver. |  | 1.30 |  | Remark
CJV300 Installation Report | [23 empty] | 1.0
■ | Fill out this report for new installed machine and send it to the following address or Fax.
| Address: | [8 empty] | Fax: |  |  |  | Email:
| Installation Date |  |  |  | Company |  |  |  |  | Dealer / Person in Charge |  |  |  | Country | [5 empty] | Customer Detail
(yyyy/mm/dd)
| Machine Model |  |  |  | Serial Number |  |  |  | Initial Firmware |  | Updated Firmware |  |  |  |  | Ink Type |  |  |  | Ink Set
| CJV300 |  |  | □-130 □-160 |  |  |  |  | Ver. |  | Ver. |  |  |  |  | □ |  |  |  | □ | 4 color | □ | 4 color+Dk
[20 empty] | □ | 8 color | □ | 6 color
[20 empty] | □ | 6 color+ W
[20 empty] | □ | 6 color+ Si,W
[20 empty] | □ | 6 color+ Dk
| RIP Software, Cutting Software | [11 empty] | Main Material
| □ | Mimaki RLP |  |  |  | □ | Other RIP：[ ] | [5 empty] | Name：[ ]
| □ | RasterLink Serial number: [ ] | [10 empty] | Product Code：[ ]
□ Perform the education about the risk on the operation of machine described in “ Safety Precautions ”.
A) | □ | Installation went well without problems
B) | □ | Inspected the installation site
| 1. | Installation Environment
|  | □ | There is chemical material around the installation site. Chemical type is [ ].
|  | □ | There was unpleasant odor other than the ink。Cause of the odor is [ ].
|  | □ | Please fill in the following information.
|  |  | ■ Ambient Temperature [ ] ℃ | [6 empty] | ■ Humidity [ ] %Rh |  |  |  |  | ■ Power Supply [ ] Volt
C) | □ | When you execute FCO announced at installation,please fill it out.
|  |  | FCO No |  |  |  |  | Content of FCO | [10 empty] | Comment
|  | □ | FCO
|  | □ | FCO
|  | □ | FCO
|  | □ | FCO
|  | □ | FCO
D) | □ | There were problem during installation. (*Please fill in the following details)
| 1. | Packaging and Accessories Check
|  | □ | Damages on the Packing Box [ □ Main Unit Box ]
|  | □ | Damages, prominent scratches or permanent dirt on the Machine [ □ Main Unit □ Stand Assy]
|  | □ | The accessories parts were missing.（*Please refer to Accessories List for details）
|  |  | □ | Check the box on the missing parts in the Accessories List and attached the list to this report.
| 2. | Power ON, Initial ink filling and Machine movement
|  | □ | Unable to turn ON the machine, or showing ERROR [ ] at power ON.
|  | □ | Initial ink filling sequence unable to give perfect nozzles in TEST DRAW.
|  | □ | Please simply indicate the nozzles condition using below figure.
| □Nozzle Missing □Nozzle Deflection □Color Mixing | [6 empty] | □Nozzle Missing □Nozzle Deflection □Color Mixing | [7 empty] | ■ | Procedures taken to improve the nozzles
condition to 100%.
[17 empty] | □ | SOFT CLEANING [ ] time(s)
[17 empty] | □ | Capping Adj. [Mechanical or Operation]
[17 empty] | □ | NORMAL CLEANING [ ] time(s)
[17 empty] | □ | Replace or adjust the Ink Valve
[17 empty] | □ | HARD CLEANING [ ] time(s)
[17 empty] | □ | Head replacement
[17 empty] | □ | Wash or Manual Cleaning
[17 empty] | □ | Other [ ]
|  | □ | PC connection failure due to USB driver.
| 3. | Print Quality
|  | □ | Need to Re-adjust the Slant Adjustment (Service Mode).
|  | □ | Need to Re-adjust the FEED COMP 2 (Service Mode).
|  | □ | Another Maintenance adjustment [ ] was re-adjusted.
© 2014 MIMAKI ENGINEERING CO.,LTD. | [13 empty] | CJV300 Installation Report | [7 empty] | R.1.0 |  | P.1

## Inst-RPT-E (2_JV)
INSTALLATION CHECKLIST > CJV300 Installation Report | [9 empty] | Rev.
Model |  | CJV300 | Issued | 2014.09.01 | Revised | F/W ver. | 1.30 | Remark
CJV300 Installation Report | [9 empty] | 1.0
E) | Please write down below any advice or comment.
© 2014 MIMAKI ENGINEERING CO.,LTD. | [6 empty] | CJV300 Installation Report |  | R.1.0 | P.2